CDTA COMMITTEE AGENDA

Planning and Stakeholder Relations Committee

Thursday, February 22, 2018

Start Time - 12:00 PM; Anticipated End Time – 1:00 PM

110 Watervliet Avenue

Committee Item	Responsibility

Call to Order	Joe Spairana

Ascertain Quorum	Joe Spairana

Agenda Approval	Joe Spairana

Approve Minutes of January 25, 2018	Joe Spairana

Consent Agenda Items

- None

Administrative Discussion Items

- Capital Projects Update	Ross Farrell

- FY2019 Budget Development*	Mike Collins

Governance/Policy Issue Discussion Items

Executive Session

None

Next Meeting Date:  March 22, 2018

Adjourn

* Indicates Material (Or Additional Material) Will Be Provided at Meeting

Capital District Transportation Authority

Planning and Stakeholder Relations Committee

Meeting Minutes – January 25, 2018 at Noon at the 110 Watervliet Avenue Office

In Attendance:  Joe Spairana (Chair), Denise Figueroa, Georgie Nugent, Jayme Lahut, Mark Schaeffer,

Corey Bixby, Carm Basile, (CEO), Chris Desany, Amanda Avery, Jaime Watson, Sarah Matrose,

Lance Zarcone, Mark Wos, Lauren Bailey, Erika Reilly, Trish Cooper, Dan Holdsworth, Phil Parella,

Fred Gilliam, Ross Farrell, Thomas Guggisberg, Jonathan Scherzer, Kathy Colbert

Meeting Purpose

This was the regular monthly meeting of the Planning Committee.

Consent Agenda Items

Approve Taxi MOU’s with Local Municipalities - Lauren Bailey

Lauren Bailey presented a status report on the taxi oversight project and a description of the Memoranda of Understanding for the Cities of Saratoga Springs and Troy.  Progress was made with other municipalities to adopt the common ordinance, and staff will insure administrative tasks continue.  The next step requires a Board resolution to support the MOUs.

The Committee recommends authorizing the execution of an MOU for the Cities of Saratoga Springs and Troy to perform taxi-related administrative services.

FY2019 Budget Development – Phil Parella

Phil Parella presented a budget update, highlighting our major revenue sources with a focus on the federal 5307 program.  Over the past 5 years, the Governor and Legislature have supported transit by increasing State Operating Assistance by 17% and enacting a 5-year Capital Program.

The majority of our federal funding comes through 5307, referred to in our budget as federal maintenance.  Although the purpose of 5307 is for capital investments, we can reallocate these funds into our operating budget as long as it supports federal assets.

As the budget development process continues, we will fine tune expenses and provide options to close the budget deficit.

Potential 2018 Service & Project Considerations - Ross Farrell

Ross Farrell presented service planning projects under consideration for 2018.   Examples include new service along route 9 between Latham and Clifton Park; modifying New Scotland Avenue service; express service between Troy, Colonie Center and Crossgates Mall; and service reductions where ridership is not meeting expectations.

Uncle Sam Update - Chris Desany

Chris Desany gave an update on the Uncle Sam transit center.  A public hearing was held in November, and the determination and findings were approved by the Board in December.

The land owner has exercised his right to file for a judicial review. This petition challenges the proceedings, and this was expected.  We will prepare a response for the court and may require additional action by the Board.

Navigator Update - Jon Scherzer

Jon provided an update on the transition to the Navigator smartcard and mobile ticketing platform that took place on January 1, 2018.   This includes;

- Exchange policy to convert leftover magnetic striped media

- April 1 is the final switchover date

- 15,000 customers are now registered Navigator users.

Adjournment and Next Meeting

The next meeting of the Committee will be held at noon on February 22, 2018 at 110 Watervliet Avenue.

Respectfully submitted by Michael P. Collins:

_______________________________________

Capital Projects Report

February 2018

BusPlus Blue Line

River Corridor Bus Rapid Transit

Description – This project calls for a 17-mile Bus Rapid Transit line on Routes 4 and 32, connecting Albany, Menands, Watervliet, Troy, Cohoes and Waterford.

Status – The project was accepted into the Federal Transit Administration’s (FTA) Small Starts program in July 2014 and received federal environmental clearance in 2016.  A consultant team was selected in 2015 to complete all activities related to design, engineering, and land acquisition.

As part of the regional Transportation Improvement Program administered by Capital District Transportation Committee (CDTC), a “BRT Setaside” was established allowing CDTA $13 million toward construction of elements of the BusPlus Blue Line and BusPlus Purple Line.

A multifaceted application called a “Project Rating Package” was submitted to the FTA in September 2016 for Small Starts funding in federal fiscal year 2018.  The project was rated a Medium making it eligible for federal funding.  CDTA submitted an updated Project Rating Package in September 2017 for federal fiscal year 2019.  Earlier this month, the project was again rated a medium. However, Presidential appropriations for the Small Starts program remain in question.

Construction for eight of the thirty-one Blue Line stations is nearing completion.  These stations and the Uncle Sam Transit Center are now subprojects targeted for earlier implementation (discussed later in this report).  Additional subprojects are currently being designed to determine capital costs and they will be built when funding is available.

In May, CDTA submitted a grant application for $7.31 million to the Upstate Revitalization Initiative (URI) administered by NYS Empire State Development (ESD).  The application was shortlisted and additional information is being provided to ESD for a final decision.  If awarded, this funding would possibly allow CDTA to implement a “BRT-lite” which would be a scaled down version of the Blue Line.

Upcoming Milestones

- Spring 2018 – Announcement of URI funding

- Late 2018 – Announcement of FY19 Small Starts funding (if not obtained for FY18)

Project Cost

- $40-$45 million for full BRT with Small Starts funding (excluding subprojects)

- $20-$30 million for BRT lite without Small Starts funding (excluding subprojects)

TAP Stations

BusPlus Blue Line Subproject

Overview – Construction of eight stations is approaching completion in advance of the remaining BusPlus Blue Line.  This includes site work, traffic signal upgrades, and pedestrian infrastructure improvements to existing stops with high ridership.

Status – In November 2015, CDTA was awarded a grant for partial funding of the project from the NYS Department of Transportation’s Transportation Alternative Program (TAP). No land acquisition was required and construction will be completed by May.

Upcoming Milestones

- May 2018 – Complete construction

Project Cost – $2.7 million

- $2.05M from TAP grant

- Remainder from BRT Setaside

Uncle Sam Transit Center

BusPlus Blue Line Subproject

Overview – A transit center adjacent to the Uncle Sam parking garage in Downtown Troy will be constructed in advance of the remaining BusPlus Blue Line.  This includes construction of an enclosed 1,500 sq. ft. passenger facility, staging area for five buses, contraflow bus lanes, and improvements to multiple intersections for efficient bus routing and pedestrian safety.

Status – The eminent domain process is proceeding as discussed.

Upcoming Milestones

- September 2018 – Obtain property, transfer required land to City of Troy, and release bids

- Winter 2018 – Select contractor and begin construction

- Late Fall 2019 – Begin operations

Project Cost – $6-$8 million depending on bid pricing

- $650,000 from Empire State Development

- Remainder from BRT Setaside and internal funds

Additional Blue Line Subprojects

The following is a list of subprojects that CDTA is continuing to design in hopes they are incorporated into other construction projects adjacent to future BRT station sites.

- Jay Street Station – Sitework related to BRT station in North-Central Troy as part of Capital Roots expansion.

- Riverview Center Station – Sitework and queue jump lanes related to a station in Menands as part of NYSDOT’s roadway reconstruction of a segment of NY Route 32.

- 111th Street Station – Sitework related to station in Lansingburgh as part of City of Troy’s reconstruction of Powers Park.

- Livingston Station – Coordination of designs with a new apartment building north of downtown Albany by private developer to ensure area for future station.

- Hedley Park Station – Complete design to ensure possible parking garage by private developer does not prevent future station construction.

- Congress Street – Sitework for station in downtown Troy as part of mixed-use private development on former Keybank property.

- Downtown Cohoes Station – Continue coordination with City of Cohoes on reconstruction of Remsen Street.

BusPlus Purple Line

Washington/Western Bus Rapid Transit

Description – This project calls for an 8-mile Bus Rapid Transit line on Washington & Western Avenues, connecting Downtown Albany, the Harriman Office Complex, the University at Albany, SUNY Polytechnic and Crossgates Mall.

Status – The project was accepted into the FTA Small Starts program in 2014 and in 2015 the project received federal environmental clearance.  A consultant team was selected in 2015 to complete all activities related to design, engineering, and land acquisition.  As part of the regional Transportation Improvement Program administered by CDTC, a “BRT Setaside” was established allowing funding towards construction of elements of both the Purple Line and Blue Line.

Station site work and pedestrian infrastructure has been completed at six of the sixteen BRT stations.  Detailed design has been completed for three additional stations, at least one of which will be constructed in advance of the remainder of the BRT line (discussed later in this report).  Preliminary engineering is complete for the Crossgates Mall Transit Center, Harriman-UAlbany busway, and all other stations.

A Project Rating Package was submitted in September for FTA Small Starts funding in FY19.  Earlier this month, a Medium rating was given and this makes the project eligible for Small Starts funding, although Presidential appropriations for the Small Starts program remain in question.

Upcoming Milestones

- Late 2018 – Announcement of FY19 Small Starts funding if included in Congressional budgets

Project Cost – $65-$110 million depending on scope, funding source, and contributions from partners

Washington Avenue Transit & Pedestrian Improvement Project

BusPlus Purple Line Subproject

Overview – A BRT station and transportation improvements to five city blocks in Albany will be constructed in advance of remaining Purple Line.  The project allows for more efficient bus routing, improved passenger waiting facilities, and reductions in accidents.  This includes significant improvements for other travel modes including pedestrian safety and vehicular traffic flow.

Status – A series of public meetings were held in 2015 and the final concept completed in spring 2016 which accommodated comments received.  In June 2016, CDTA was awarded a grant for partial funding of the project from the NYS Department of Transportation’s Highway Safety Improvement Program (HSIP).

Construction began in July 2017.

Upcoming Milestones

- June 2018– Complete construction

Project Cost – $1.7 million

- $770,000 from HSIP

- Remainder from BRT Setaside

UAlbany Downtown Campus

BusPlus Purple Line Subproject

Overview – Extending west from the Washington Avenue project, an additional BRT station and four city blocks of transportation improvements will be constructed in advance of the Purple Line.  The project will include station site work and pedestrian improvements while allowing for efficient bus routing and limiting impacts to on-street parking.  The University at Albany is in process of a multiyear expansion of its Downtown Campus and is promoting alternative transportation modes to limit parking demand.

Status – Detailed design has been completed for CDTA’s project components and we are in the process of designing the additional components requested by UAlbany.

Upcoming Milestones

- Spring / Summer 2018 – Release bids and hire contractor

- Summer 2018 - Begin construction

- Summer 2019 – Complete construction

Project Cost – $1-$3 million depending on scope and partner contributions

- Funding awarded from URI

- Remainder From BRT Setaside

Harriman West / UAlbany ETEC Station

BusPlus Purple Line Subproject

Overview – A future BRT station and part of the Harriman-UAlbany busway may be constructed prior to the BusPlus Purple Line.   The project includes bus and pedestrian only connections between the Harriman and University at Albany Uptown campuses by redesigning roadway adjacent to the future ETEC academic building.   ETEC is an expansion of the Uptown Campus on to the Harriman Campus – its goal is to limit parking and increase travel to the site by foot, bike, and bus.

Status – Advanced design has been completed and was approved by the NYS Office of General Services and NYS Department of Transportation.  Preliminary construction of the ETEC site and installation of utilities is in progress.  Final design of the station will be completed in 2019, construction in 2020, and will be operational in 2021.

Upcoming Milestones

- 2018/2019 – Progress design in parallel with ETEC project

- 2020 – Begin and complete construction

- 2021 – Begin operations with opening of ETEC building

Project Cost – $2.75 million

- Approximately $950,000 by University at Albany

- Remainder by BRT Setaside, internal funds, or possibly Small Starts

BRT Lite Subprojects for Purple Line

The following is a list of subprojects that CDTA is progressing, with lower cost designs as potential alternatives if funding from Small Starts is not provided.

- Crossgates Mall Improvements – Reduce project scope to no longer build a transit center, but provide a larger station with improved amenities for waiting customers.  This includes minor roadway/intersection improvements to allow for more efficient bus routing on the mall’s property.

- UAlbany Busway – Reduce project scope to build busway only on eastern side of campus between ETEC / Harriman West station to the Campus Center.  This will allow for local bus routes to provide direct connections between the Uptown Campus, ETEC, the Alumni Quad dormitory, and Downtown Campus

- Harriman East Station – Provide infrastructure for buses traveling from the Uptown Campus / ETEC through Harriman Campus to stop near State office buildings.